## Sheet1
№ | Tasks | Members | Start Time | End time | Designations
1 | Problem Analysis and gathering information | Nukenov Anuar, Assylzhan Balatursyn | 2020-10-05 | 2020-10-31 | Achived | In Progress | Rejected | In the plan
2 | UML model of our project | Nukenov Anuar, Assylzhan Balatursyn | 2020-11-01 | 2020-11-30
3 | Database design | Zholbaryskhan Shorakhan | 2020-12-01 | 2020-12-06
4 | Database creation | Zholbaryskhan Shorakhan | 2020-12-07 | 2020-12-18
5 | Optimizing database queries | Erbosyn Azamat | 2020-12-19 | 2020-12-29
6 | Back-end: Create order functional | Nukenov Anuar | 2021-01-04 | 2021-01-18
7 | Back-end: Registration and login system | Zholbaryskhan Shorakhan | 2021-01-04 | 2021-01-24
8 | Back-end: User profile and User capabilities | Assylzhan Balatursyn | 2021-01-24 | 2021-02-07
9 | Back-end: Share Registry system | Erbosyn Azamat | 2021-01-19 | 2021-02-07
10 | Back-end: Integration with Registry | Erbosyn Azamat | 2021-02-08 | 2021-02-21
11 | Back-end: Refactoring | Zholbaryskhan Shorakhan | 2021-02-08 | 2021-02-21
12 | Back-end: Swagger for testing REST-API | Nukenov Anuar | 2021-02-21 | 2021-03-07
13 | Dev-ops containerizing services and using docker | Assylzhan Balatursyn | 07/0321 | 2021-03-22
14 | Front-end: UX analysis | Zholbaryskhan Shorakhan | 2021-03-22 | 2021-03-28
15 | Front-end: UI design | Zholbaryskhan Shorakhan | 2021-03-29 | 2021-04-04
16 | Front-end: GUI implementation | Erbosyn Azamat | 2021-05-04 | 2021-04-18
17 | Testing and debugging | Nukenov Anuar, Assylzhan Balatursyn, Shorakhan Zholbaryskhan, Erbosyn Azamat | 2021-04-19 | 2021-05-31